## Sheet1
UK Sport Major Events Application
Delivery Milestone Tracker
Name of Event: | I.e. Judo World Cup
Date of Event: | I.e. October 2017
Document Version and Date: | I.e. V1 02.07.17
Guidance
The Delivery Milestone Tracker is designed to ensure key milestones for your event(s) are identified.
This tracker should be used throughout the planning of your event and be reviewed at your Stakeholder Board meetings.
This tracker focuses on the milestones that will be tracked at Stakeholder Board level. This document can be expanded into a project plan containing all event milestones for use with your LOC.
The year/month/week requirements should be appropriate to the planning timescales of your event i.e. a 4 year planning window may not be appropriate.
The milestones listed will also form part of the award letter issued in relation to the UK Sport funding should the application process be successful.
Milestone Date
Milestone Group | Delivery Milestone
Award | All major public funding confirmed | e.g. July 2017
UK Sport Conditions of Award met
Objectives tracker approved
Cashflow agreed
IF | Host contract signed
Governance | Governance plan in place
Conflicts of Interest on SHB agenda and registered
Hosting responsibilites and IF Contract reporting
Terms of reference agreed and in place
Event Planning | Event project plan agreed
Competition schedule agreed
Procurement plans in place
Venue | Venue contract signed
Site plan agreed
People | Organisational structure agreed by SHB Board
Senior executive appointed
Functional heads appointed
Volunteers recruited and scheduled
Hospitality plan in place
Accommodation & Transport | Accommodation contracted/delivery agency contracted
PR, Marketing and Commercial | Marketing plan approved
Commercial plan approved
Sponsorship contracts received
Tickets on sale
Spectator experience plan in place
Broadcast and Presentation | TV production company appointed
Domestic broadcast rights awarded
Sports presentation contract appointed
Risk | Event contingency plan approved
Event insurances in place - Cancellation, liability etc
Readiness plan agreed
Legacy | Legacy group operational
Event objectives approved
Bespoke